## Slide 1
GROWTH PLAN: WORKSHOP CAMPAIGN SPRINT
Build Your First AI Project in 60 Minutes
Target: 500 Final-Year Engineering Students (CSE/IT/AI-ML) | 7-Day Sprint | Budget: ₹2,000
GOAL & AUDIENCE
500 Registrations
Targeting 4th year CSE, IT, and AI & ML students seeking hands-on project portfolio additions.
SPRINT TIMELINE
7 Days Execution
Fast daily velocity pacing (~71 regs/day) with continuous performance review and channel reallocation.
BUDGET & UNIT ECONOMICS
₹2,000 Total Budget
Target Blended CAC of ₹4.00/student. Micro-testing prevents ad burn and protects runway.
STRATEGIC GROWTH THESIS: WHY A GROWTH TRACKER OVER A LANDING PAGE?
• Attribution over Assumptions: A static landing page cannot identify which campus batch group or ambassador drives signups.
• Strict CAC Discipline: With ₹2,000 for 500 students (allowable CAC = ₹4), uncalibrated ad spend leads to rapid capital exhaustion.
• Real-Time Velocity Steering: Measuring daily signup pacing (71/day) enables course-correction before the 7-day sprint ends.
• High-Leverage Zero-Cost Funnels: Campus ambassadors and WhatsApp communities drive 70% of registrations at zero marginal ad spend.

## Slide 2
ACQUISITION ARCHITECTURE
4-Channel Marketing Mix (Target = Exactly 500)
01
College Ambassadors
Target: 200 Regs (40%)
Est. CAC: ₹2.50 / student
DESCRIPTION & DEMOGRAPHIC:
On-ground student leaders in CSE/IT departments across 5 colleges (IIT-H, NIT-W, CBIT, VNR, JNTU). Unique codes (CAMP101-105).
GROWTH TACTIC:
Micro-incentives: Amazon vouchers for top 3 ambassadors crossing 40 registrations.
02
WhatsApp Communities
Target: 150 Regs (30%)
Est. CAC: ₹0.80 / student
DESCRIPTION & DEMOGRAPHIC:
Direct drops in 3rd & 4th year batch groups, placement prep channels, and college coding club communities.
GROWTH TACTIC:
Hook: "Build an AI project to add to your resume before final campus placements begin."
03
Instagram Promotions
Target: 75 Regs (15%)
Est. CAC: ₹10.60 / student
DESCRIPTION & DEMOGRAPHIC:
Micro-budget paid ads and student creator reel partnerships targeted at engineering hubs.
GROWTH TACTIC:
A/B micro-tests: 15-second VS Code screen recording demonstration of the AI project.
04
Personal & Peer Referrals
Target: 75 Regs (15%)
Est. CAC: ₹1.30 / student
DESCRIPTION & DEMOGRAPHIC:
Student-to-student viral loops and departmental mailing list forwards.
GROWTH TACTIC:
"Invite 2 batchmates to build together" prompt triggered immediately post-registration.

## Slide 3
FINANCIAL RIGOR & UNIT ECONOMICS
₹2,000 Budget Allocation & Burn Protection
Expense Category | Allocated | % Share | Operational Objective
Instagram Promotion Test | ₹800 | 40% | Phased A/B micro-campaigns testing video CTR vs carousel
Promotional Content Assets | ₹300 | 15% | Figma templates, motion graphic teaser, and WhatsApp flyer packs
Ambassador Incentives | ₹500 | 25% | Amazon gift vouchers for top 3 campus leads crossing targets
Contingency Reserve | ₹400 | 20% | Guarded buffer reserved for scaling top channel on Day 5-6
Total Campaign Budget | ₹2,000 | 100% | Blended Cost Per Acquisition (CAC): ₹4.00 per student
UNIT ECONOMICS DISCIPLINE
₹4.00 Max Allowable CAC
• ₹2,000 ÷ 500 students = ₹4.00 blended CAC target.
• Paid ads alone in tech cost ₹15-₹30/lead; relying purely on paid ads would yield only 70-130 students.
• Combining organic ambassador virality (₹0 marginal CAC) with paid testing balances unit economics.
DYNAMIC OVERSPEND PROTECTION
Budget Safety Alerts
• Micro-test staging: Initial ad test capped at ₹350 on Day 2 before further allocation.
• Dynamic alert banner triggers at 80% burn rate (₹1,600 spent with >2 days left).
• Hard stop warning if total logged expenses exceed ₹2,000 threshold.

## Slide 4
OPERATIONAL EXECUTION TIMELINE
7-Day Sprint Execution Schedule & Milestones
D1
Prep & Setup
35 Regs
KEY ACTIVITIES:
Finalize tracking UTMs, Figma posters, and onboard 3 campus leads.
D2
Outreach Blitz
95 Regs
KEY ACTIVITIES:
Activate 15 batch WhatsApp groups; deploy ₹350 Instagram micro-test.
D3
Social Proof
180 Regs
KEY ACTIVITIES:
Evaluate Ad Test A; release mid-week ambassador referral leaderboard.
D4
Mid-Sprint Audit
290 Regs
KEY ACTIVITIES:
Current Day: 284 regs recorded (56.8%); trigger peer referral challenge.
D5
Channel Review
390 Regs
KEY ACTIVITIES:
Reallocate ₹200 from contingency to top-performing ambassador hubs.
D6
Urgency Drive
460 Regs
KEY ACTIVITIES:
"Seats Filling Fast" countdown across batch groups and status stories.
D7
Final Push & Lock
500 Regs
KEY ACTIVITIES:
Final 6-hour broadcast, cross 500 registrations, award ambassador prizes.

## Slide 5
GROWTH INTELLIGENCE & VERIFICATION
Measurement Engine, Referral Attribution & Live Asset
CAMPUS AMBASSADOR ATTRIBUTION ENGINE
Dynamic attribution calculated from registration records (not hardcoded):
Ambassador | College | Code | Signups | % Total
Rahul Sharma | IIT Hyderabad | CAMP101 | 28 | 9.9%
Sneha Patel | NIT Warangal | CAMP102 | 25 | 8.8%
Priya Rao | CBIT Hyderabad | CAMP103 | 24 | 8.5%
Aditya Verma | VNR VJIET | CAMP104 | 22 | 7.7%
Ananya Reddy | JNTU College | CAMP105 | 20 | 7.0%
Key Takeaway: Ambassadors deliver zero-marginal-ad-spend registrations and drive over 40% of all registrations.
WORKING ASSET & VERIFICATION METRICS
LIVE VERCEL PRODUCTION DEPLOYMENT
https://nxtwave-growth-tracker-99fxwr60t-bindhuuuu.vercel.app/
GITHUB REPOSITORY & AUTOMATION TESTS
https://github.com/Bindhuuuu/NxtWave-Growth-Tracker
• 23/23 Automated Unit Tests Passing (100%)
• TypeScript strict compile: 0 errors
Core Technical Differentiators:
1. Duplicate email prevention across 284+ student records.
2. Reactive metric recalculations on record addition/deletion.
3. Rule-based growth engine + "What-If" scenario sandbox.
4. Client-side localStorage persistence with 1-click demo reset.